## Sheet1
Title Action | Timing | Responsible Unit | Indicator(s) / Target | Current Status / Update
1.1 Integration of the national Policy on RI principles into DCU internal Code of Good Research Practice | Q4 2015 | RIS | 100% complete (ongoing) | Code of Good Research Practice, Research Misconduct Policy and Code of Practice on Authorship in place. Continuous monitoring & improving
1.2 Develop and implement mechanisms to embed the principles of Ireland’s National Policy on RI across DCU | Ongoing | RIS | 100% complete (ongoing) | RI Training Programme http://www.dcu.ie/graduate_research/Research-Integrity-Training-Programme.shtml-1 has been jointly developed by RIS and the Graduate Studies Office. Compulsory for PhD students.
2.1 DCU undertakes to make public its internal processes in relation to ethics approval processes in DCU. | Q2 2016 | RIS | 100% complete | A statement about DCU approach to RI/Ethics now externally accessible on the DCU website https://www4.dcu.ie/research/Research-Integrity-DCU.shtml
2.2 Improvement internal accessibility to guidelines and information in relation to the use of animals in research. | Q4 2016 | RIS | 100% complete | Policy for Research using animals approved, website for internal processes created https://www.dcu.ie/researchsupport/news/2016/Oct/New-DCU-Policy-for-Use-Animals-for-Scientific-or-Educational-Purposes, new Animal Welfare Body established.
3.1 Induction Information for new researchers to increase awareness of their professional responsibilities. | Q1 2016, Q1 2017, Q1 2018 | HR | 100% complete | The Policies section of the DCU website has a starter pack www4.dcu.ie/policies/policy-starter-packs.shtml which is specific to new research staff with relevant policies. In addition the DCU HR section of the website has an information page for new researchers www.dcu.ie/hr/training/orientationforresearchers.shtml
4.1 New IT system to increase compliance with internal approval processes for research projects. | Q4 2016 (*new timeline of Q3 2018) | RIS | 50% complete | First phase achieved. Roll out to staff expected in Q2 2018 due to technical issues
4.2 Increase awareness among researchers of their obligations in relation to their funded research. | Q3 2016 | RIS | 100% complete | PI alerted to their responsibilities upon award. Research related policies accessible from website under www4.dcu.ie/policies/policy-starter-packs.shtml. In addition there is a regular Newsletter issued from the Research Innovation Office providing information to the Research and overall University Community
6.1 Better procedures and guidelines for researchers re. responsibility for accountability in their research. | Q4 2017 | RIS, GSO, Finance | 50% complete | The STEP centralised research administration unit assists with financial management and accountability of research projects and assist with compliance with the funding body's terms and conditions. The university is also in the process of upgrading the research application and awards management system which when finish will provide researchers with an excellent tool to manage the financial issues associated to research projects. The Code for Good Research Practice has been updated to align it with the National Guidelines for Research Integrity and we have issued a new code of practice on Authourship. In addition he Research Ethics Committee (REC) provide guidelines on the ethics application process on their webpages. The REC have also begun developing their own guideline statements on particular areas of research, in order to better inform researchers on how to approach ethical issues - these will be available on the website also. The REC are moving to a logic based online application form in Sept 2017, which will better guide the applicant in providing the key information regarding their intended research project. These measures will assist researchers in the ethical conduct of their research project and associated considerations regarding data management and retention.
6.2 DCU will conduct an audit of current practices in relation to retention of research data -best practice | Q4 2016 | RIS, ISS,Library | 100% complete | Survey on research data management completed. A number of RDM Resources now available via the Research Integrity webpage https://www.dcu.ie/researchsupport/research_integrity.shtml
8.1 Open access publication and DCU’s process for exploiting research results- improved guidance |  | RIS Library | 100% complete | New IP policy approved and on website https://www4.dcu.ie/sites/default/files/policy/54_intellectual_property_policy_vpri_v2.0.pdf Statement on Open Access is now also published on the website https://www.dcu.ie/library/information/researchers/open-access.shtml
9.1 Communication of research to non-expert audiences - increase awareness of existing training ops |  | HR, RIS | 100% complete | Maximising your Research Profile + Communications Training for Researchers and Academics courses available. In addition there is a regular Newsletter from the Research Innovation Office providing information to the Research and overall University Community (Appendix 1)
11.1 Ensure full implementation of existing PMDS, Probation procedures and support systems and continue to monitor completion rates for PMDS and Probation reviews. | Q4 2017 | HR | 20% complete | A working group in HR has been established to update the database (90%) so HR processes, including probation and PMDS, can managed more thoroughly. Implementation of Probation/PMDS will focus on meeting the 2017/2018 deadline.
13.1 Conduct an initiative to encourage the adoption of the Guide of Good Practice in the Recruitment and Selection of Research Students. |  | GSO | 100% complete | DCU Guide of Good Practice Published https://www4.dcu.ie/ sites/default/files/graduate_research/Guidance%2520notes% 2520for%2520recruitment%2520of%2520research%2520students.docx+&cd=1&hl=en&ct=clnk&gl=ie
14.1 Integrate Unconscious Bias training into the initiatives that support the recruitment and selection process. | Q2 2016 | HR | 100 % complete (ongoing) | Training for APC, Review Boards complete. Training including for interview panel members is ongoing
14.2 Revise professional development (Interviewing, Supervision) for PIs to include reference to the DCU Guide of Good Practice in the Recruitment GSO, HR and Selection of Research Students |  | GSO, HR | 100% complete | DCU Guide of Good Practice Published https://www4.dcu.ie/ sites/default/files/graduate_research/Guidance%2520notes% 2520for%2520recruitment%2520of%2520research%2520students.docx+&cd=1&hl=en&ct=clnk&gl=ie
21.1 Complete the process to communicate the explicit aims, purpose and benefits of the Research Career Framework (RCF), including the context in which the RCF operates, to ensure continuous and sustained understanding by all stakeholders. |  | HR | Ongoing | DCU Institute of Education and Business fully briefed in May, 2017. Re-engagement required with other Faculties
23.1 Improve communication to researchers of the researcher training and development opportunities offered by the University. |  | HR, RIS | HR - Ongoing RIS - Complete | HR with RIS make regular communications via the RIS newsletter and specific mailing lists. HR will be conducting a review with PIs and Post Docs with the focus on their PD needs and effectiveness of the current research development programme commencing on 29th May 2017.
23.2 DCU will develop and implement a research infrastructure management plan |  | RIS | 100 % complete (ongoing) | Research Infrastructure Policy available on the Policies section of the DCU website https://www4.dcu.ie/sites/default/files/policy/175_-_research_infrastructure_policy_v1_0.pdf
27.1 Review actions identified for HR and RIS that arise from the submission for the Athena SWAN award. |  | HR, RIS | 100 % complete (ongoing) | DCU awarded the Athena Swan Bronze in March 2017 . In January 2017 a Head of Diversity and Inclusion was appointed to manage this process under the direction of HR Director and VP for Research.
28.1 Include the research community in the University’s Mentoring Scheme. | Q4 2017 | HR | 100 % complete (ongoing) | DCU mentoring scheme extended to all staff in September 2016 https://www.dcu.ie/hr/training/mentoring.shtml. A mid-term evaluation will be conducted with the mentoring pairs in June 2017 with a final evaluation in December 2017. An additional training session on mentoring for postdoctoral researchers will be run in June 2017.
28.2 Enhance career support services for all researchers. | Q4 2016 | RIS, HR, GSO,SSD | 100 % complete (ongoing) | The four University functions of Human Resources, Research and Innovation Support, Graduate Studies and Student Support and Development continue to make good progress on career supports for researchers. The University Research Development Programme, aimed at supporting the professional development on researchers and academic staff in research is revised year on year and new modules addes to address the needs of the instution. For example, new modules have been added post-incorporation to address the needs of the newly acquired staff who have different needs in relation to their research activity.
30.1 Analyse further, data from the Performance Management Development Scheme to ensure researcher professional development needs are being met | Q4 2017 | HR | HR - Ongoing | Database now updated for targeted communication. (Will require support from other key stakeholders.)
31.1 DCU will update and monitor its policies in relation to intellectual property to ensure consistency with national best practices and update as required. | 2017, 2018 | RIS | 100 % complete | IP policy now live on the Policies section of the DCU website https://www4.dcu.ie/sites/default/files/policy/54_intellectual_property_policy_vpri_v2.0.pdf
32.1 DCU will complete institutional guidelines on authorship that will include reference to co-authorship and a complaints procedure to mediate author disputes. | Q4 2015 | RIS | 100 % complete | Action completed and approved by the Research Committee. DCU’s Code of Practice on Authorship was approved by the university on 18 November 2015, it is available for download in Website
33.1 In co-operation with the Teaching Enhancement Unit (TEU), further develop existing professional development supports for teaching and learning. | Q2 2016 | HR, TEU | 100 % complete (ongoing) | The Teaching Enhancement unit together with L&D offer two courses to support the PD of research staff in teaching and learning.
33.2 Conduct an audit of School’s policies for PG research learning support activities |  | GSO | 100 % complete (ongoing) | Each School now has in place a “structured pathway” which directs students to a range of module and training modules.
36.1 Ensure PIs and Supervisors utilise existing Performance Management Development Scheme to identify appropriate training and development requirements for researchers | Q4 2017 | HR | HR - Ongoing | Communication regarding the Research Career Framework (RCF) and related HR Processes e.g. Probation, PMDS has been reviewed. A number of systems gaps have been identified. This includes initial communication to the postdoctoral researcher about both the RCF and related HR Processes. A working group within HR has been established to work on ensuring HR database is up to date.
36.2 Review the communication of the roles and responsibilities of the key stakeholders in the RCF | Q3 2017 | HR | HR - Ongoing | Communication regarding the Research Career Framework (RCF) and related HR Processes e.g. Probation, PMDS has been reviewed. A number of systems gaps have been identified. This includes initial communication to the postdoctoral researcher about both the RCF and related HR Processes. A working group within HR has been established to work on ensuring HR database is up to date.
37.1 Enhance Leadership and Management Training and Development interventions for Senior Researchers and PIs | Q4 2017 | HR | 100 % complete (ongoing) | Professional Development programmes– Professional Skills for Research Leaders (blended learning) and the University Leadership and Management Development Programme (blended learning), Project Management for Researchers