## 2022 - Template
DCU Risk Register Template
Guide on how to populate each of the panels on a unit Risk Register
Prepared by: The DCU Risk & Compliance Officer, January 2022, (Contact Ext. 8706)
Risk Register
Unit Name: Insert Unit Name Here
Year: | Indicate to which year the register is for
Status: Draft or Final
Unique DCU Register Ref | Units Own Register Ref | Risk Description | Current Controls - Controls and / or actions already in place or taken | Primary Impact Category | Impact | Likelihood | Risk Weighting (I x L) | L / M / H | Movement in Year | Treat or Tolerate | Risk Owner | Future Controls - Further Controls / Actions Required (FARs) | FAR Action Owner (Individual's Title or Group Name) | Date | Risk Officers Queries
1.1 (Note 1) | 1 (Note 2) | Concentrate on: a) defining the risk; b) the cause of the risk; c) explaining its impact. | List here the various actions or controls which are up & running now and which are actively addressing the risk as stated. These actions and controls should seek reduce the impact if the risk occurs and/or reduce the likelihood that a risk will occur. | (Note 3) | 4 (Note 4) | 5 (Note 5) | 20 (Note 6) | H (Note 7) | (Note 8) | (Note 9) | (Note 10) | (Note 11) | (Note 12) | (Note 13) | (Note 14)
1.2 | 2 |  |  |  | 3 | 4 | 12 | M
1.3 | 3 |  |  |  | 2 | 3 | 6 | L
Emerging Risks | [6 empty] | Note 5 | The likelihood of a risk should also be indicated. This is a very subjective assessment as it is rarely possible to predict the future with any certainty. However
Ref | Risk Description | [6 empty] | each unit should make an attempt to indicate how likely it is that a defined risk may arise. The higher the number, the more likely it is. A guide to the likelihood options is
1 | (Note 15) | [6 empty] | shown in the 'Likelihood' key table above.
2
3 | [6 empty] | Note 6 | This is a calculated figure got from multiplying the value given in adjacent cells for impact & likelihood. The higher the figure the more serious the risk.
4
[7 empty] | Note 7 | Risks are sorted into 3 separate categories as follows based on their risk weighting:
Key to Impact Levels | [8 empty] | (Note 8): H; (Note 9): = High level risk - those with a value of 16 or higher
[9 empty] | M | = Medium level risk - those with a value of 8 to 15
Level | Impact Level | [7 empty] | (Note 8): L; (Note 9): = Low level risk - those with a value of 1 to 7
1 | Minor
2 | Limited | [5 empty] | Note 8 | This indicates whether the risk has changed since the previous review in terms of its risk weighting e.g. Increase / Decrease / No Change
3 | Serious
4 | Very serious | [5 empty] | Note 9 | Treat or Tolerate: For each risk a decision should be made by the unit as to whether it requires further mitigation or not. It is likely that for
5 | Catastrophic | [6 empty] | low level risks no further action is needed or desirable. For all higher level and upper level medium risks it is likely that further
mitigating actions are needed. These actions will be listed in the "Further Controls / Actions Required" panel. See note 10.
Key to Likelihood Levels
[7 empty] | Note 10 | Risk Owner: This will be the administrative unit, management position, individual or group who is in the best position to address the risk
Level | Likelihood Level | [6 empty] | on an on-going basis.
1 | Rare (20 years and over)
2 | Unlikely (10 - 20 Years) | [5 empty] | Note 11 | Further Controls / Actions Required: List here those actions or controls which could be applied to the risk which would lower its impact
3 | Possible (5 - 10 Years) | [6 empty] | were it to materialise or decrease the likelihood that a risk will materialise. When controls / actions listed here eventually become active they
4 | Likely (1 - 5 Years) | [6 empty] | can be reallocated to the "Controls and / or Actions already in place or taken - current controls" panel.
5 | Already happening or within one year
[7 empty] | Note 12 | Ideally the job title of the individual (or the group name in some cases) who will be responsible for getting the further actions / controls
Note 1 | The unique register reference is used to maintain an audit trail of all risks and should not be changed. As some risks will be deleted over time it is important that the | [6 empty] | listed in the adjacent panel up and running should be inserted here, where known. The individual or group should have the level of
| reference number attached to a risk is not removed. All sub-units will have been assigned an overall reference number, which is the number before | [6 empty] | authority to actively initiate and manage the roll out of the actions listed in the "Further Controls / Actions Required" panel.
the decimal point, (e.g. Finance Office is # 1) while the number after the decimal point denotes the risk's reference within the risks for that unit. e.g. "1.12" refers
| to the 12th risk in the Finance office register. The first risk in the HR office will be 2.1 and so on. As new risks are added to the unit registers they will be given the | [5 empty] | Note 13 | The expected date of when the point(s) noted in the "Further Controls / Actions Required" panel will be in place should be inserted
| next number in sequence. | [6 empty] | in this panel. Depending on how the action point is described this could be the date when the further action is initiated or when it will
actually be delivered and addressing the risk as stated.
Note 2 | The risk reference for the unit's own purposes. It will always be a sequential number on the face of the unit's register e.g. 1,2,3,4,5 & so on.
[7 empty] | Note 14 | This panel is used by the Risk Officer to list any questions he/she may have in relation to the risk. It is used primarily when preparing for
Note 3 | In this panel please insert one of the following impact categories which fits best with the nature of the risk referred too i.e. the 'Primary Category': | [6 empty] | the annual risk register update. Ideally the answers given here, if relevant, should be worked into the body of the risk register. This
| a) Strategic | c) Operational | [5 empty] | panel does not form part of the final risk register for the unit concerned.
| b) Financial | d) Reputational
| Further guidance on selecting the correct impact category, i.e. the definitions of each of the impact options in the context of the nature of the risk under consideration, | [5 empty] | Note 15 | This panel is used to document any 'Emerging Risks' i.e. those risks for which it is not yet possible to document their nature / impact in
| can be obtained from the document titled 'Unit Level Impact Assessment Criteria' which will be included in the annual risk reporting pack sent to Heads of Unit. | [6 empty] | detail but which should, nevertheless, be brought to the attention of senior management through the risk process.
Note 4 | The potential impact of the risk should be indicated using one of the potential impact options in the 'Impact' key table above. The selected level of impact for a
unit level Risk Register should be from the perspective of the unit's local management.